## Summary
ERM Gap Analysis Scorecard
Current solution benchmarked against Corporater ERM and the world-class ERM/GRC field
Prepared 8 August 2026 ¦ Companion to 00_ERM_REMODEL_MASTER_PLAN.md and 01_EXECUTION_PROMPT_PACK.md
Coverage by domain
Domain | Items | Strong | Present | Partial | Mock | Absent | Covered (Strong+Present) | Coverage % | Weighted coverage % | P0 | P1
A. Platform architecture & data model | 25 | 0 | 0 | 7 | 0 | 18 | 0 | 0% | 11.2% | 2 | 13
B. Risk taxonomy, register & appetite | 22 | 1 | 4 | 7 | 1 | 9 | 5 | 22.73% | 32.95% | 0 | 14
C. Assessment, analysis & methodology | 23 | 2 | 2 | 5 | 0 | 14 | 4 | 17.39% | 24.78% | 1 | 6
D. Risk quantification | 18 | 1 | 1 | 6 | 0 | 10 | 2 | 11.11% | 23.61% | 0 | 2
E. Controls & control monitoring | 20 | 2 | 2 | 2 | 0 | 14 | 4 | 20% | 22.5% | 0 | 3
F. Compliance, obligations & regulatory change | 18 | 0 | 1 | 3 | 1 | 13 | 1 | 5.556% | 11.67% | 0 | 5
G. Policy management | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0% | 0% | 0 | 0
H. Internal audit & assurance | 18 | 0 | 1 | 2 | 0 | 15 | 1 | 5.556% | 9.167% | 0 | 0
I. Incidents, events, issues & actions | 16 | 5 | 6 | 1 | 1 | 3 | 11 | 68.75% | 65.94% | 0 | 1
J. Third-party & supply chain risk | 19 | 0 | 0 | 0 | 0 | 19 | 0 | 0% | 0% | 0 | 0
K. Operational resilience & BCM | 17 | 0 | 0 | 0 | 0 | 17 | 0 | 0% | 0% | 0 | 0
L. ESG & sustainability | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0% | 0% | 0 | 0
M. Strategy & performance | 14 | 0 | 0 | 1 | 0 | 13 | 0 | 0% | 2.857% | 0 | 1
N. Reporting, dashboards & analytics | 17 | 0 | 0 | 4 | 0 | 13 | 0 | 0% | 9.412% | 2 | 6
O. AI & intelligent automation | 18 | 0 | 0 | 4 | 3 | 11 | 0 | 0% | 9.722% | 3 | 0
P. Integration & data | 16 | 0 | 0 | 1 | 0 | 15 | 0 | 0% | 2.5% | 1 | 5
Q. UX, configurability & accessibility | 16 | 0 | 0 | 1 | 0 | 15 | 0 | 0% | 2.5% | 0 | 10
R. Security, administration & platform governance | 17 | 0 | 0 | 5 | 0 | 12 | 0 | 0% | 11.76% | 5 | 2
S. Deployment, delivery & commercial | 10 | 0 | 0 | 2 | 0 | 8 | 0 | 0% | 8% | 1 | 2
T. Nigeria & Africa environment (our own domain) | 24 | 1 | 0 | 3 | 0 | 20 | 1 | 4.167% | 9.167% | 1 | 12
TOTAL | 350 | 12 | 17 | 54 | 6 | 261 | 29 | 8.286% | 13.81% | 16 | 82
Coverage by capability class
Class | Meaning | Items | Covered | Coverage %
TS | Table stakes — absence disqualifies you | 130 | 25 | 19.23%
D | Differentiator — separates good from average | 163 | 4 | 2.454%
LE | Leading edge — few vendors have it in 2026; where you can win | 57 | 0 | 0%
Backlog by priority
Priority | Meaning | Items
P0 | Blocker — unsellable / unsafe until fixed (Phase 0) | 16
P1 | Parity — required to match Corporater (Phases 1-2) | 82
P2 | Moat — where we win (Phases 3-4) | 145
P3 | Beyond — deferrable | 107
How to read this
• Current state assessed from a full read of all 60 migrations, routes/web.php, 20 models, 10 of 14 services and targeted controller method bodies, then independently re-verified against the codebase claim by claim.
• Coverage % counts only Strong + Present. Weighted coverage % scores Strong 1.00, Present 0.85, Partial 0.40, Mock 0.05, Absent 0.00.
• 'Mock' means the feature renders but the numbers are fabricated (mt_rand). Mock is scored below Partial deliberately — it is worse than absent because it is a reputational risk.
• Corporater column reflects their published solution feature list, solution brief and product screenshots. 'Unknown' means not evidenced publicly.
• Domain T is our own addition — the Nigerian and African environment requirements that no global checklist covers, and where the durable moat is.
• Work package references map to 01_EXECUTION_PROMPT_PACK.md.

## Scorecard
# | Domain | Capability | Class | Corporater | Current state | Priority | Work package | Evidence / note
1 | A. Platform architecture & data model | Metadata-driven object model; new fields without code deployment | TS | Yes | Absent | P1 | WP-03, WP-05 | No metadata layer; all fields are DDL columns
2 | A. Platform architecture & data model | Configurable object types (not just fields) | D | Yes | Absent | P1 | WP-03, WP-05 | entity_types carries only icon/color/level — no attribute schema
3 | A. Platform architecture & data model | Configurable, typed relationships between any object types | D | Yes | Absent | P1 | WP-03 | Relationships are hardcoded pivots
4 | A. Platform architecture & data model | Digital-twin org graph (entity, division, BU, process, system, asset, product, geography) | LE | Yes | Partial | P1 | WP-03 | entities/entity_types is an embryonic version; runs in parallel with business_units — two org models
5 | A. Platform architecture & data model | Object inheritance/templating so common behaviour is defined once | TS | Yes | Absent | P1 | WP-03
6 | A. Platform architecture & data model | Period-aware measure model shared by KPIs and KRIs | D | Yes | Absent | P1 | WP-04 | Risk scores are single-valued; no period dimension anywhere
7 | A. Platform architecture & data model | Point-in-time reconstruction of any object's state ('as at' queries) | D | Yes | Absent | P1 | WP-04 | Reconstructable only indirectly from risk_assessments
8 | A. Platform architecture & data model | Full versioning and immutable audit trail on every object and field | TS | Yes | Partial | P0 | WP-00, WP-03 | Field-level trail exists but is broken: AuditTrailService writes 'Risk', Risk::auditTrail() queries 'risk'
9 | A. Platform architecture & data model | Soft delete, archival, configurable retention policies | TS | Yes | Partial | P2 | WP-03 | softDeletes on users/entities only; no retention policy
10 | A. Platform architecture & data model | Hierarchical roll-up and aggregation derived from the graph | D | Yes | Partial | P1 | WP-03 | Risk::calculateRollUpScore() exists but is risk-specific, not graph-derived
11 | A. Platform architecture & data model | Multi-entity / multi-org support with data segregation | TS | Yes | Partial | P0 | WP-00 | organization_id on every table but ZERO global scopes; 166 uses of '?? 1' across 22 files; MonteCarloService line 49 reads scenarios with no org filter
12 | A. Platform architecture & data model | Multi-tenancy with per-tenant configuration divergence | D | Yes | Absent | P1 | WP-05
13 | A. Platform architecture & data model | Configurable lifecycle states and status models per object type | TS | Yes | Absent | P1 | WP-03 | Status is a hardcoded enum/string per table
14 | A. Platform architecture & data model | Calculated/derived fields with a formula engine | D | Yes | Absent | P1 | WP-04, WP-05 | Needed for inflation-indexed thresholds
15 | A. Platform architecture & data model | Configuration as a versioned artefact with dev->test->prod promotion, diff, rollback | D | Unknown | Absent | P2 | WP-05 | Where most configurable platforms fail — real differentiator
16 | A. Platform architecture & data model | Bulk import/export at object level with validation and error reporting | TS | Yes | Partial | P1 | WP-02, WP-07 | CSV only; xlsx accepted but parsed with fgetcsv; insert-only, no dry-run, no rollback
17 | A. Platform architecture & data model | Reference/content library with versioned framework packs | D | Yes | Absent | P2 | WP-16 | The moat, productised
18 | A. Platform architecture & data model | Graph query capability exposed to users and AI agents | LE | No | Absent | P3 | WP-03, WP-07
19 | A. Platform architecture & data model | Horizontal scalability; documented performance limits | TS | Yes | Absent | P2 | WP-07 | No load testing; Monte Carlo runs synchronously in HTTP
20 | A. Platform architecture & data model | Sub-second response on registers of 100k+ objects | D | Unknown | Absent | P2 | WP-09
21 | A. Platform architecture & data model | Localisation of the object model (labels, taxonomies, content per language) | TS | Yes | Absent | P2 | WP-09 | No lang/ directory; 28 __() calls across 142 views
22 | A. Platform architecture & data model | Currency handling with FX rates by period | D | Unknown | Absent | P2 | WP-04, WP-15 | loss_events.currency is the only currency field and is unused
23 | A. Platform architecture & data model | Sandbox / what-if branching | LE | No | Absent | P3 | WP-05
24 | A. Platform architecture & data model | Event-sourced change log enabling replay | LE | No | Partial | P3 | WP-03 | domain_events outbox exists with retry counters
25 | B. Risk taxonomy, register & appetite | Central risk register with configurable fields | TS | Yes | Present | P1 | WP-05 | Register is strong; fields are not configurable
26 | B. Risk taxonomy, register & appetite | Configurable multi-level risk taxonomy (3+ levels) | TS | Yes | Present | P1 | WP-10 | risk_categories: self-tree, level, materialized path, cbn_mapping_code, basel_category
27 | B. Risk taxonomy, register & appetite | Multiple simultaneous taxonomies on one risk | D | Yes | Absent | P1 | WP-10 | One category_id only; risk_taxonomies is a disconnected parallel tree with its own live UI
28 | B. Risk taxonomy, register & appetite | Risk hierarchy — parent/child, aggregation into themes and principal risks | TS | Yes | Strong | P3 | - | parent_risk_id, risk_level, hierarchy_path, roll_up_weight, calculateRollUpScore()
29 | B. Risk taxonomy, register & appetite | Risk ownership with named accountable individual and delegation | TS | Yes | Present | P3 | - | risk_owner_id + risk_steward_id; entities have delegate_owner_id
30 | B. Risk taxonomy, register & appetite | Cause -> risk event -> consequence structure | TS | Yes | Absent | P1 | WP-10 | A risk is a title plus scores; ISO 31000 requires structure
31 | B. Risk taxonomy, register & appetite | Opportunity modelling alongside threat (ISO 31000 bidirectional) | D | Yes | Absent | P1 | WP-10 | Corporater ships an opportunity heat map; we have no opportunity model at all
32 | B. Risk taxonomy, register & appetite | Inherent, current/residual and target risk levels | TS | Yes | Partial | P1 | WP-10 | target_rating is a STRING LABEL ONLY — no target L/I/score, so target cannot be plotted
33 | B. Risk taxonomy, register & appetite | Risk velocity, persistence and proximity attributes | D | Unknown | Partial | P2 | WP-10 | risk_velocity exists; proximity and persistence do not
34 | B. Risk taxonomy, register & appetite | Emerging risk register distinct from the principal register | TS | Yes | Mock | P1 | WP-02, WP-10 | ai/radar page is mt_rand-generated
35 | B. Risk taxonomy, register & appetite | Configurable likelihood and consequence scales with definitions per point | TS | Yes | Absent | P1 | WP-05 | 5x5 hardcoded in 3 places; settings written but read by nothing
36 | B. Risk taxonomy, register & appetite | Multi-dimensional consequence categories | TS | Yes | Present | P2 | WP-05 | financial/operational/reputational/regulatory (+strategic on assessments)
37 | B. Risk taxonomy, register & appetite | Scales configurable per organizational unit and per risk type | D | Unknown | Absent | P2 | WP-05
38 | B. Risk taxonomy, register & appetite | Risk appetite statements as first-class objects linked to objectives | TS | Yes | Partial | P1 | WP-10 | Keyed to risk_category_id only; not linked to objectives or nodes
39 | B. Risk taxonomy, register & appetite | Quantified appetite/tolerance thresholds with automatic breach detection | D | Yes | Partial | P1 | WP-10 | Single tolerance band; RiskAppetiteService reads 5 columns that do not exist - capacity, appetite_type and notes are always fallbacks
40 | B. Risk taxonomy, register & appetite | Currency-denominated appetite with stated probability of exceedance | LE | No | Absent | P2 | WP-10, WP-18 | White space; unlocked by quantification L5
41 | B. Risk taxonomy, register & appetite | Risk appetite cascade — group appetite decomposed to BU limits | D | Unknown | Absent | P1 | WP-10 | entities.category_appetites exists but is unused
42 | B. Risk taxonomy, register & appetite | Risk interdependency / correlation mapping | D | Yes | Partial | P2 | WP-03 | risk_related_risks with relationship_type + correlation_strength
43 | B. Risk taxonomy, register & appetite | Risk network visualisation showing contagion and concentration | LE | No | Absent | P3 | WP-08
44 | B. Risk taxonomy, register & appetite | Risk acceptance workflow with sign-off, expiry and re-review | TS | Yes | Absent | P1 | WP-10 | treatment_strategy can be 'accept' with zero governance
45 | C. Assessment, analysis & methodology | Configurable assessment campaigns with scheduling and reminders | TS | Yes | Present | P2 | - | assessment_campaigns -> campaign_assignments -> campaign_responses
46 | C. Assessment, analysis & methodology | RCSA with full lifecycle (scope, distribute, respond, challenge, sign-off) | TS | Yes | Partial | P0 | WP-02, WP-11 | RcsaController::storeWorksheet() IS A STUB — submissions silently discarded
47 | C. Assessment, analysis & methodology | Prior-period pre-population with change highlighting | D | Yes | Absent | P1 | WP-11 | Requires the period model
48 | C. Assessment, analysis & methodology | Second-line challenge and override workflow | D | Yes | Absent | P1 | WP-11
49 | C. Assessment, analysis & methodology | Questionnaire builder with conditional logic, scoring and weighting | TS | Yes | Partial | P1 | WP-11 | Schema is AHEAD of market (8 types, conditional_logic, scoring_rules); UI is 915 bytes
50 | C. Assessment, analysis & methodology | Heat maps with configurable axes, bubble sizing and drill-through | TS | Yes | Partial | P1 | WP-08, WP-11 | Hardcoded 5x5; no cell counts; no drill-through
51 | C. Assessment, analysis & methodology | Heat map movement / trend visualisation across periods | D | Yes | Absent | P1 | WP-04, WP-08
52 | C. Assessment, analysis & methodology | Native bow-tie with barriers, escalation factors and barrier effectiveness | D | Unknown | Partial | P2 | WP-11 | Read-only and derived — buildCauses()/buildConsequences() synthesize nodes
53 | C. Assessment, analysis & methodology | FMEA/FMECA with SxOxD, RPN and AIAG-VDA Action Priority | D | Unknown | Absent | P2 | WP-11
54 | C. Assessment, analysis & methodology | HAZOP with node/parameter/guide-word structure | D | No | Absent | P3 | WP-11 | Relevant for energy and manufacturing customers
55 | C. Assessment, analysis & methodology | Root cause analysis (5 Whys, fishbone) | TS | Yes | Strong | P3 | - | loss_event_rca with why_1..why_5, contributory factors, own approval chain
56 | C. Assessment, analysis & methodology | Fault tree and event tree analysis | D | No | Absent | P3 | WP-11
57 | C. Assessment, analysis & methodology | Scenario analysis with workshop capture, participants and approval | TS | Yes | Partial | P2 | WP-18 | quantification_scenarios has calibration and approval fields
58 | C. Assessment, analysis & methodology | Structured expert elicitation with calibration training and bias controls | D | No | Absent | P3 | WP-18
59 | C. Assessment, analysis & methodology | Control effectiveness feeding residual risk transparently | TS | Yes | Strong | P3 | - | Weighted aggregation via control_weight; but TWO conflicting effectiveness maps exist
60 | C. Assessment, analysis & methodology | Assessment quality analytics — outlier, boilerplate, peer comparison | D | No | Absent | P2 | WP-11
61 | C. Assessment, analysis & methodology | AI-assisted RCSA — draft, flag inconsistencies, summarise challenge | LE | No | Absent | P2 | WP-29 | Attacks the biggest quality problem in ERM; almost nobody does it well
62 | C. Assessment, analysis & methodology | Assessment audit trail — who scored what, when and why | TS | Yes | Present | P3 | - | risk_assessments with rationale, justification, previous_assessment_id chain
63 | C. Assessment, analysis & methodology | Delphi / multi-round anonymous estimation | D | No | Absent | P3 | WP-11
64 | C. Assessment, analysis & methodology | Maturity assessments against framework principles | TS | Yes | Absent | P2 | WP-11 | COSO ERM 20 principles, COSO IC 17 principles, ISO 31000 clauses, NIST tiers
65 | C. Assessment, analysis & methodology | Assurance mapping across the three lines with coverage and gap view | D | Yes | Absent | P2 | WP-24
66 | C. Assessment, analysis & methodology | Automatic detection of over-assurance and assurance gaps | LE | No | Absent | P3 | WP-24
67 | D. Risk quantification | Semi-quantitative currency ranges on impact | TS | Yes | Partial | P1 | WP-05 | financial_exposure_ngn exists; scale points carry no currency bands
68 | D. Risk quantification | Expected loss calculation (frequency x severity) | TS | Yes | Strong | P3 | - | expected_annual_loss_kobo on scenarios
69 | D. Risk quantification | Monte Carlo engine with configurable iterations and seeds | D | Yes | Present | P1 | WP-18 | 10,000 iterations default; RUNS SYNCHRONOUSLY IN THE HTTP REQUEST; no seed control
70 | D. Risk quantification | Distribution library (PERT, triangular, lognormal, Poisson, neg-binomial, Weibull, Pareto, GPD, empirical) | D | Unknown | Partial | P2 | WP-18 | Poisson + Lognormal ONLY in code; columns exist for binomial/Pareto/GPD/Weibull
71 | D. Risk quantification | Distribution fitting to historical loss data with goodness-of-fit | D | No | Absent | P2 | WP-18 | We have the loss data to fit to — real advantage
72 | D. Risk quantification | FAIR-conformant decomposition (TEF, Vuln, PL, SLEF, SLM, six loss forms) | D | No | Absent | P2 | WP-18 | Corporater has no evidence of FAIR
73 | D. Risk quantification | FAIR-CAM control analytics | LE | No | Absent | P3 | WP-19
74 | D. Risk quantification | FAIR-MAM materiality assessment | LE | No | Absent | P3 | WP-19
75 | D. Risk quantification | Loss exceedance curves as a primary board visual | D | No | Absent | P2 | WP-18 | Should replace the heat map as the board visual
76 | D. Risk quantification | ALE, VaR and CVaR/Expected Shortfall at configurable confidence levels | D | Partial | Partial | P2 | WP-18 | VaR at 90/95/99/99.9 exists; CVaR does not
77 | D. Risk quantification | Portfolio aggregation with correlation (rank correlation, copulas) | LE | No | Absent | P2 | WP-19 | correlation_method DEFAULTS TO 'GAUSSIAN_COPULA' but NO COPULA IS IMPLEMENTED
78 | D. Risk quantification | Sensitivity / tornado analysis | D | Yes | Absent | P2 | WP-18 | Corporater ships EBITDA/FCF/NPV tornado bars
79 | D. Risk quantification | Control ROI / cost-benefit optimisation | LE | No | Absent | P2 | WP-19 | 'This N400m control reduces 95th-percentile loss by N3.1bn' sells the product
80 | D. Risk quantification | Scenario-based stress testing and reverse stress testing | D | Yes | Partial | P2 | WP-19 | stress_multiplier_* and stress_config are STORED AND NEVER APPLIED
81 | D. Risk quantification | LDA — separate frequency/severity, EVT/POT tails, convolution | D | No | Absent | P2 | WP-19 | What a Nigerian bank's ICAAP Pillar 2 actually needs
82 | D. Risk quantification | Combining internal loss data, external loss data, scenarios and BEICFs | D | Unknown | Partial | P2 | WP-19 | Internal loss data is strong; external and BEICFs absent
83 | D. Risk quantification | Backtesting quantified estimates against realised losses | LE | No | Absent | P2 | WP-19 | What makes quantification credible to a regulator
84 | D. Risk quantification | Capital calculation support (Basel SMA, Solvency II SCR) | LE | Partial | Partial | P2 | WP-19 | ICAAP model is correctly structured but Pillar 2A/2B are INPUT fields, not derived
85 | E. Controls & control monitoring | Central control library with configurable attributes | TS | Yes | Present | P2 | WP-05 | control_type/nature/frequency/automation_level are free-form strings, no vocabulary
86 | E. Controls & control monitoring | Control classification (preventive/detective, manual/automated, key/non-key) | TS | Yes | Present | P2 | - | is_key_control on the pivot; classification columns unconstrained
87 | E. Controls & control monitoring | Control-to-risk mapping, many-to-many, with stated mitigation effect | TS | Yes | Strong | P3 | - | risk_control_mapping with control_weight and is_key_control — better than most tools
88 | E. Controls & control monitoring | Control-to-obligation/framework mapping, multi-framework | TS | Yes | Absent | P1 | WP-20
89 | E. Controls & control monitoring | Common control model — one control satisfying N requirements, tested once | D | Yes | Absent | P1 | WP-03, WP-20 | Requires typed relationships
90 | E. Controls & control monitoring | Separate design effectiveness and operating effectiveness | TS | Yes | Partial | P2 | WP-10 | control_tests.test_type includes both but effectiveness is one rating
91 | E. Controls & control monitoring | Control testing workflow with sampling, evidence, conclusion, reviewer sign-off | TS | Yes | Strong | P3 | - | 4 test types, 4 results, full lifecycle, tester/reviewer separation, evidence upload
92 | E. Controls & control monitoring | Control deficiency evaluation with escalation to material weakness | TS | Yes | Absent | P2 | WP-10
93 | E. Controls & control monitoring | Control owner attestation/certification cycles | TS | Yes | Absent | P2 | WP-21
94 | E. Controls & control monitoring | Control test scripting/automation against source systems | D | No | Absent | P2 | WP-25
95 | E. Controls & control monitoring | Continuous control monitoring with scheduled automated tests | D | No | Absent | P2 | WP-25 | Corporater gap; Forrester says this is where the market is heading
96 | E. Controls & control monitoring | Full-population testing rather than sampling | D | No | Absent | P3 | WP-25
97 | E. Controls & control monitoring | Exception auto-generation into the issue register with owner and SLA | D | Yes | Absent | P2 | WP-25
98 | E. Controls & control monitoring | Control health score as a continuous time series feeding residual risk | LE | No | Absent | P2 | WP-04, WP-25 | Natural once controls are measures
99 | E. Controls & control monitoring | Automated evidence capture with immutable provenance and hash | D | No | Absent | P2 | WP-25
100 | E. Controls & control monitoring | ITGC support and SOD analysis | TS | Yes | Absent | P2 | WP-25
101 | E. Controls & control monitoring | SOD ruleset management with conflict detection across ERP roles | D | Unknown | Absent | P3 | WP-25
102 | E. Controls & control monitoring | Control effectiveness dashboards by entity, process and framework | TS | Yes | Partial | P1 | WP-08 | testing-dashboard.blade.php is 4.7 KB
103 | E. Controls & control monitoring | Control rationalisation analytics (redundant, over-tested, unmitigating) | LE | No | Absent | P3 | WP-25
104 | E. Controls & control monitoring | Control coverage gap detection (risks above appetite with no effective control) | LE | No | Absent | P2 | WP-10 | High value, low effort once appetite is quantified
105 | F. Compliance, obligations & regulatory change | Regulatory obligation register at requirement/clause level | TS | Yes | Absent | P1 | WP-20 | regulatory_circulars tracks documents, not obligations
106 | F. Compliance, obligations & regulatory change | Obligation -> policy -> control -> risk -> process linkage chain | TS | Yes | Absent | P1 | WP-20 | The compliance spine
107 | F. Compliance, obligations & regulatory change | Multi-framework support with cross-mapping | TS | Yes | Partial | P1 | WP-20 | regulatory_risk_mapping exists; no framework model
108 | F. Compliance, obligations & regulatory change | Pre-built framework content library | TS | Yes | Absent | P2 | WP-17 | ISO/NIST/COSO/COBIT/PCI/SOC2/GDPR/DORA/NIS2/SOX
109 | F. Compliance, obligations & regulatory change | Framework version management and migration mapping | D | Unknown | Absent | P3 | WP-20 | e.g. ISO 27001:2013 -> 2022
110 | F. Compliance, obligations & regulatory change | Compliance obligation ownership and periodic attestation | TS | Yes | Absent | P2 | WP-20, WP-21
111 | F. Compliance, obligations & regulatory change | Compliance calendar with regulatory deadlines and filing tracking | TS | Yes | Present | P2 | WP-16 | regulatory_deadlines + regulatory_filings; UI is minimal (1.8 KB calendar view)
112 | F. Compliance, obligations & regulatory change | Regulatory change feed ingestion from external providers | D | Yes | Absent | P3 | WP-29
113 | F. Compliance, obligations & regulatory change | Jurisdiction/entity/product applicability filtering | D | Yes | Absent | P2 | WP-20 | Critical for Nigerian holdcos with multiple licences
114 | F. Compliance, obligations & regulatory change | AI regulatory change impact analysis — obligation-level diff | LE | Partial | Mock | P3 | WP-29 | ai/regulatory-pulse is mt_rand-backed
115 | F. Compliance, obligations & regulatory change | Regulatory horizon scanning with a 'coming into force' pipeline | D | Yes | Absent | P3 | WP-29
116 | F. Compliance, obligations & regulatory change | Regulatory interaction/examination management | TS | Yes | Partial | P1 | WP-20 | issues.cbn_examination_finding exists; no examination object
117 | F. Compliance, obligations & regulatory change | Regulatory reporting pack generation (ICAAP, ORSA, self-assessment) | D | Yes | Partial | P1 | WP-12, WP-16 | ICAAP model exists; output is CSV
118 | F. Compliance, obligations & regulatory change | DORA Register of Information generation | D | Yes | Absent | P3 | WP-22 | EU-specific; low priority for Nigeria
119 | F. Compliance, obligations & regulatory change | Conflicts of interest, gifts & hospitality registers | D | Yes | Absent | P3 | WP-20
120 | F. Compliance, obligations & regulatory change | Whistleblowing / speak-up case management | D | Yes | Absent | P3 | WP-20
121 | F. Compliance, obligations & regulatory change | Conduct risk / individual accountability responsibility maps | D | Yes | Absent | P3 | WP-20 | CBN org-structure model is the Nigerian equivalent
122 | F. Compliance, obligations & regulatory change | AI control-to-framework auto-mapping with confidence scores | LE | No | Absent | P2 | WP-29 | Makes the standards packs compound
123 | G. Policy management | Policy repository with version control and a single published version | TS | Yes | Absent | P2 | WP-21 | Module entirely absent
124 | G. Policy management | Authoring, review, approval, publication and archival workflow | TS | Yes | Absent | P2 | WP-21 | Module entirely absent
125 | G. Policy management | Policy hierarchy — policy -> standard -> procedure -> work instruction | TS | Yes | Absent | P2 | WP-21 | Module entirely absent
126 | G. Policy management | Attestation/acknowledgement campaigns with tracking and escalation | TS | Yes | Absent | P2 | WP-21 | Module entirely absent
127 | G. Policy management | Policy-to-obligation, policy-to-control and policy-to-risk mapping | TS | Yes | Absent | P2 | WP-21 | Module entirely absent
128 | G. Policy management | Scheduled review cycles with owner reminders and overdue escalation | TS | Yes | Absent | P2 | WP-21 | Module entirely absent
129 | G. Policy management | Targeted distribution by role, entity, geography or job family | D | Yes | Absent | P3 | WP-21 | Module entirely absent
130 | G. Policy management | Exception/waiver workflow with expiry and compensating control | D | Yes | Absent | P2 | WP-21 | Module entirely absent
131 | G. Policy management | Policy portal with search, readability and mobile access | D | Yes | Absent | P3 | WP-21 | Module entirely absent
132 | G. Policy management | AI policy gap analysis and AI-drafted policy updates | LE | Yes | Absent | P3 | WP-21 | Module entirely absent
133 | H. Internal audit & assurance | Audit universe with auditable entities and risk-based scoring | TS | Yes | Absent | P2 | WP-24
134 | H. Internal audit & assurance | Risk-based annual audit plan with resource and capacity planning | TS | Yes | Absent | P2 | WP-24
135 | H. Internal audit & assurance | Multi-year plan and coverage analysis against the risk register | TS | Yes | Absent | P3 | WP-24
136 | H. Internal audit & assurance | Engagement management — scope, objectives, budget, team, timeline | TS | Yes | Absent | P2 | WP-24
137 | H. Internal audit & assurance | Risk and control matrix (RACM) per engagement | TS | Yes | Absent | P2 | WP-24
138 | H. Internal audit & assurance | Electronic workpapers with cross-referencing and review notes | TS | Yes | Absent | P2 | WP-24
139 | H. Internal audit & assurance | Finding/observation management with rating, root cause, management response | TS | Yes | Partial | P2 | WP-24 | issues module covers findings but there is no audit engagement context
140 | H. Internal audit & assurance | Issue and action tracking to closure with validation testing | TS | Yes | Present | P2 | WP-24 | Issues module is strong — reuse it rather than duplicating
141 | H. Internal audit & assurance | Audit report generation with configurable templates | TS | Yes | Absent | P2 | WP-24
142 | H. Internal audit & assurance | Time tracking, timesheets and auditor utilisation | D | Yes | Absent | P3 | WP-24
143 | H. Internal audit & assurance | IIA Global Internal Audit Standards (2024) conformance tracking | D | Yes | Absent | P3 | WP-24
144 | H. Internal audit & assurance | QAIP — internal and external quality assessment records | D | Yes | Absent | P3 | WP-24
145 | H. Internal audit & assurance | IIA Topical Requirements support | D | Yes | Absent | P3 | WP-24
146 | H. Internal audit & assurance | Audit committee reporting pack with plan status and issue ageing | D | Yes | Partial | P2 | WP-24 | Board report exists but emits CSV
147 | H. Internal audit & assurance | Data analytics integration over full populations | D | Yes | Absent | P3 | WP-24
148 | H. Internal audit & assurance | Combined assurance map across three lines plus external providers | D | Yes | Absent | P2 | WP-24
149 | H. Internal audit & assurance | Continuous auditing with analytics between engagements | LE | Yes | Absent | P3 | WP-24
150 | H. Internal audit & assurance | AI-drafted audit programmes and AI-summarised findings | LE | Yes | Absent | P3 | WP-24
151 | I. Incidents, events, issues & actions | Incident capture with configurable forms and multi-channel intake | TS | Yes | Present | P1 | - | Web only today; USSD/WhatsApp is WP-14
152 | I. Incidents, events, issues & actions | Incident triage, severity classification and routing | TS | Yes | Present | P3 | - | event_severity, customer_impact_rating, staged approval
153 | I. Incidents, events, issues & actions | Investigation workflow with root cause analysis | TS | Yes | Strong | P3 | - | loss_event_rca with 5-Whys, own approval, remediation actions
154 | I. Incidents, events, issues & actions | Loss event data capture — gross loss, recoveries, net loss | TS | Yes | Strong | P3 | - | FIVE-WAY recovery decomposition + full insurance claim lifecycle
155 | I. Incidents, events, issues & actions | Date of occurrence / discovery / accounting captured separately | TS | Yes | Strong | P3 | - | date_of_loss, date_discovered, date_reported
156 | I. Incidents, events, issues & actions | Basel 7 Level-1 event types with full L2/L3 tree and 8 business lines | D | Yes | Present | P2 | - | basel_l1/l2/l3 columns exist; the seeded tree needs completing (WP-16)
157 | I. Incidents, events, issues & actions | Boundary event handling, timing losses, rapidly recovered losses | D | Yes | Absent | P2 | - | Required for Basel-grade loss data
158 | I. Incidents, events, issues & actions | Near-miss and opportunity-cost capture flagged out of capital scope | D | Yes | Strong | P3 | - | near_misses table with control gap, investigator, conversion path
159 | I. Incidents, events, issues & actions | Grouped/related loss linkage as a single event | TS | Yes | Absent | P2 | -
160 | I. Incidents, events, issues & actions | Incident-to-risk, -to-control and -to-process linkage | TS | Yes | Strong | P3 | - | loss_event_controls with failure_type and failure_description
161 | I. Incidents, events, issues & actions | Corrective and preventive action (CAPA) with owner, due date, verification | TS | Yes | Present | P3 | - | rca_remediation_actions + issue_remediation_actions
162 | I. Incidents, events, issues & actions | Central issue/action register aggregating from all sources | TS | Yes | Present | P2 | - | issue_source tags the origin; no unified action register across modules
163 | I. Incidents, events, issues & actions | Action ageing, overdue escalation and extension approval | TS | Yes | Present | P2 | - | issue_escalation_rules is genuinely config-driven; no extension approval
164 | I. Incidents, events, issues & actions | Loss data validation and reconciliation to the general ledger | D | Yes | Partial | P2 | - | gl_account_code and cost_centre exist; no reconciliation process
165 | I. Incidents, events, issues & actions | External loss data benchmarking (ORX, ORIC) with scaling | D | Yes | Mock | P2 | WP-16, WP-29 | ai/benchmarking fabricates peer values with mt_rand(2,5)
166 | I. Incidents, events, issues & actions | AI incident similarity detection, auto-classification and duplicate merge | LE | Yes | Absent | P3 | WP-16, WP-29
167 | J. Third-party & supply chain risk | Vendor/third-party master with lifecycle states | TS | Yes | Absent | P2 | WP-22 | questionnaires.questionnaire_type has a 'vendor' value but no vendor entity exists
168 | J. Third-party & supply chain risk | Criticality tiering model with configurable scoring | TS | Yes | Absent | P2 | WP-22
169 | J. Third-party & supply chain risk | Onboarding due diligence workflow gated by tier | TS | Yes | Absent | P2 | WP-22
170 | J. Third-party & supply chain risk | Questionnaire library (SIG, CAIQ, custom) with vendor portal | TS | Yes | Absent | P2 | WP-22
171 | J. Third-party & supply chain risk | Evidence collection with certification expiry and auto-chasing | TS | Yes | Absent | P2 | WP-22
172 | J. Third-party & supply chain risk | Risk-tiered periodic reassessment scheduling | TS | Yes | Absent | P2 | WP-22
173 | J. Third-party & supply chain risk | Contract repository with key dates, renewal and termination tracking | TS | Yes | Absent | P2 | WP-22
174 | J. Third-party & supply chain risk | Contract clause and obligation extraction | D | Partial | Absent | P3 | WP-22
175 | J. Third-party & supply chain risk | Sanctions, PEP and adverse media screening with ongoing monitoring | D | Partial | Absent | P2 | WP-22
176 | J. Third-party & supply chain risk | Financial health monitoring with alerting | D | Partial | Absent | P3 | WP-22
177 | J. Third-party & supply chain risk | Continuous external security rating feeds | D | Partial | Absent | P3 | WP-22
178 | J. Third-party & supply chain risk | Concentration risk analysis by vendor, service, geography, cloud region | D | Partial | Absent | P2 | WP-22
179 | J. Third-party & supply chain risk | ESG, modern slavery and human rights due diligence | D | Partial | Absent | P3 | WP-22
180 | J. Third-party & supply chain risk | Structured offboarding with data return/deletion attestation | D | Partial | Absent | P3 | WP-22
181 | J. Third-party & supply chain risk | Nth-party mapping with single-point-of-failure detection | LE | Partial | Absent | P3 | WP-22
182 | J. Third-party & supply chain risk | Supply chain graph visualisation linked to important business services | LE | Partial | Absent | P3 | WP-22
183 | J. Third-party & supply chain risk | SBOM ingestion with component-level vulnerability propagation | LE | Partial | Absent | P3 | WP-22
184 | J. Third-party & supply chain risk | Vendor-failure scenario simulation across the dependency graph | LE | Partial | Absent | P3 | WP-22
185 | J. Third-party & supply chain risk | Nigerian agent-network modelling (exclusivity, transaction limits, principal liability) | LE | No | Absent | P2 | WP-22 | Oct 2025 Agent Banking Guidelines; networks run to hundreds of thousands of points
186 | K. Operational resilience & BCM | Important Business Service register with board-approved definitions | TS | Yes | Absent | P2 | WP-23
187 | K. Operational resilience & BCM | Impact tolerance per IBS (time-based plus other metrics) | TS | Yes | Absent | P2 | WP-23
188 | K. Operational resilience & BCM | Dependency mapping — people, premises, technology, information, third parties | TS | Yes | Absent | P2 | WP-23
189 | K. Operational resilience & BCM | Business Impact Analysis with MTPD/MAO, RTO, RPO, MBCO | TS | Yes | Absent | P2 | WP-23
190 | K. Operational resilience & BCM | Business continuity and disaster recovery plans with version control | TS | Yes | Absent | P2 | WP-23
191 | K. Operational resilience & BCM | Crisis management team structure, call trees and escalation | TS | Yes | Absent | P2 | WP-23
192 | K. Operational resilience & BCM | Exercise and test programme with results, lessons learned and actions | TS | Yes | Absent | P2 | WP-23
193 | K. Operational resilience & BCM | Severe-but-plausible scenario testing against impact tolerance | D | Yes | Absent | P2 | WP-23
194 | K. Operational resilience & BCM | Vulnerability identification and remediation from testing | D | Yes | Absent | P2 | WP-23
195 | K. Operational resilience & BCM | Self-assessment document generation with board approval | D | Yes | Absent | P3 | WP-23
196 | K. Operational resilience & BCM | ISO 22301 clause-level conformance evidence | D | Yes | Absent | P3 | WP-23
197 | K. Operational resilience & BCM | DORA CIF mapping and ICT incident classification | D | Yes | Absent | P3 | WP-23
198 | K. Operational resilience & BCM | APRA CPS 230 critical operations and tolerance levels | D | Yes | Absent | P3 | WP-23
199 | K. Operational resilience & BCM | Live dependency map refreshed from CMDB and vendor registers | LE | Yes | Absent | P3 | WP-23
200 | K. Operational resilience & BCM | Automated time-to-tolerance-breach computation | LE | Yes | Absent | P3 | WP-23
201 | K. Operational resilience & BCM | Resilience posture score with continuous monitoring | LE | Yes | Absent | P3 | WP-23
202 | K. Operational resilience & BCM | Power/diesel and connectivity modelled as first-class dependencies | LE | No | Absent | P2 | WP-23 | Nigeria's actual continuity risk; grid collapsed again in 2026, ~70% of businesses on generators
203 | L. ESG & sustainability | ESG metric library with unit management and conversion factors | TS | Yes | Absent | P3 | WP-26
204 | L. ESG & sustainability | Data collection workflow across entities with source evidence | TS | Yes | Absent | P3 | WP-26
205 | L. ESG & sustainability | Double materiality assessment (impact and financial) | TS | Yes | Absent | P2 | WP-26
206 | L. ESG & sustainability | CSRD/ESRS with datapoint tagging and phase-in reliefs | D | Yes | Absent | P3 | WP-26
207 | L. ESG & sustainability | XBRL/iXBRL digital tagging for ESRS | D | Yes | Absent | P3 | WP-26
208 | L. ESG & sustainability | ISSB IFRS S1/S2 with jurisdiction-specific modifications | D | Yes | Absent | P2 | WP-26 | Nigeria FRC roadmap: mandatory for PIEs from 1 Jan 2028; ERM framework named as a Stage 3 artefact
209 | L. ESG & sustainability | GRI, SASB, TCFD 11 disclosures, CDP | D | Yes | Absent | P3 | WP-26
210 | L. ESG & sustainability | GHG accounting — Scope 1, 2 and 3 (15 categories) | D | Yes | Absent | P2 | WP-26
211 | L. ESG & sustainability | EU Taxonomy eligibility, alignment, DNSH | D | Yes | Absent | P3 | WP-26
212 | L. ESG & sustainability | Climate scenario analysis linked to the ERM register | D | Yes | Absent | P2 | WP-26
213 | L. ESG & sustainability | Target setting and tracking (SBTi, net-zero pathways) | D | Yes | Absent | P3 | WP-26
214 | L. ESG & sustainability | Value-chain ESG data collection with assurance-grade provenance | LE | Yes | Absent | P2 | WP-26 | Nigeria's ISSA 5000 ladder reaches reasonable assurance by Year 7
213 | M. Strategy & performance | Strategic objective hierarchy cascading across the org graph | D | Yes | Absent | P2 | WP-04, WP-27
214 | M. Strategy & performance | Strategy map visualisation (Balanced Scorecard) | D | Yes | Absent | P3 | WP-04, WP-27
215 | M. Strategy & performance | OKR support alongside BSC | D | Yes | Absent | P3 | WP-04, WP-27
216 | M. Strategy & performance | KPI library with owner, target, threshold bands and frequency | TS | Yes | Absent | P2 | WP-04, WP-27
217 | M. Strategy & performance | KPI actuals capture — manual, upload and automated feed | TS | Yes | Absent | P2 | WP-04, WP-27
218 | M. Strategy & performance | Unified KPI/KRI model on one period-aware measure engine | D | Yes | Partial | P1 | WP-04, WP-27 | KRI half exists; KPI half does not. This is Corporater's 'P' in GPRC and their stated differentiator.
219 | M. Strategy & performance | KPI forecasting, trend and variance analysis | D | Yes | Absent | P3 | WP-04, WP-27
220 | M. Strategy & performance | Risk-to-objective linkage — which objectives are at risk | D | Yes | Absent | P2 | WP-04, WP-27
221 | M. Strategy & performance | Initiative/project portfolio with Gantt, milestones and phase gates | D | Yes | Absent | P3 | WP-04, WP-27
222 | M. Strategy & performance | Budget/financial linkage to initiatives and treatment cost | D | Yes | Absent | P3 | WP-04, WP-27
223 | M. Strategy & performance | Risk-adjusted performance — probability of objective achievement | LE | Yes | Absent | P3 | WP-04, WP-27
224 | M. Strategy & performance | Strategic scenario planning against the risk portfolio (COSO ERM P8) | LE | Yes | Absent | P3 | WP-04, WP-27
225 | N. Reporting, dashboards & analytics | Role-based dashboards with drill-down to source object | TS | Yes | Absent | P1 | WP-08, WP-12 | One 48.6 KB fixed dashboard; no roles, no drill-down
226 | N. Reporting, dashboards & analytics | Context-bound widgets — one definition rendering per org node | D | Yes | Absent | P1 | WP-08, WP-12 | The single biggest demo differentiator
227 | N. Reporting, dashboards & analytics | Widget library — heat map, bubble, trend, gauge, table, treemap, network, Gantt | TS | Yes | Partial | P1 | WP-08, WP-12 | Chart.js from CDN, server-fed, ~8 chart types, no interactivity
228 | N. Reporting, dashboards & analytics | User-configurable personal dashboards | TS | Yes | Absent | P1 | WP-08, WP-12
229 | N. Reporting, dashboards & analytics | Report builder with templates, filters and parameters | TS | Yes | Partial | P1 | WP-08, WP-12 | reports/custom exists; validates 4 formats and emits CSV for all of them
230 | N. Reporting, dashboards & analytics | Export to PDF, Word, Excel, PowerPoint | TS | Yes | Absent | P0 | WP-08, WP-12 | NO PDF ANYWHERE. Board/regulatory/executive reports render as on-screen views only; generateCustom validates pdf,excel,html,pptx then collapses all four to CSV
231 | N. Reporting, dashboards & analytics | Scheduled report distribution by email with bursting | TS | Yes | Absent | P2 | WP-08, WP-12 | Email is a logged placeholder (sendMailPlaceholder)
232 | N. Reporting, dashboards & analytics | Board pack generation — narrative plus visuals, versioned and approved | D | Yes | Absent | P0 | WP-08, WP-12
233 | N. Reporting, dashboards & analytics | Period-over-period comparison and movement analysis | D | Yes | Absent | P1 | WP-08, WP-12 | Requires the period model
234 | N. Reporting, dashboards & analytics | Ad-hoc query/pivot builder for end users | D | Yes | Absent | P3 | WP-08, WP-12
235 | N. Reporting, dashboards & analytics | BI tool integration with a governed semantic layer | D | Yes | Absent | P3 | WP-08, WP-12
236 | N. Reporting, dashboards & analytics | Natural-language query over the object graph with citations | LE | Yes | Absent | P3 | WP-08, WP-12
237 | N. Reporting, dashboards & analytics | NL-to-dashboard generation | LE | Yes | Absent | P3 | WP-08, WP-12
238 | N. Reporting, dashboards & analytics | AI-generated narrative commentary | LE | Yes | Partial | P3 | WP-08, WP-12 | executive-narrative LLM endpoint exists but is not UI-wired
239 | N. Reporting, dashboards & analytics | Alerting engine — threshold, trend, anomaly, event-driven, multi-channel | D | Yes | Partial | P2 | WP-08, WP-12 | In-app + DB only; email/SMS/WhatsApp modelled in prefs but unimplemented
240 | N. Reporting, dashboards & analytics | Anomaly detection on KRIs with seasonality and leading-indicator discovery | LE | Yes | Absent | P2 | WP-08, WP-12 | Computable once KRIs and loss events share the measure engine
241 | O. AI & intelligent automation | Embedded LLM assistant with organizational context | D | Partial | Partial | P2 | WP-02, WP-28, WP-29 | LlmService is well-engineered (on-prem Ollama, caching, health check)
242 | O. AI & intelligent automation | Document ingestion -> risk/obligation/control extraction with de-duplication | D | Partial | Absent | P2 | WP-02, WP-28, WP-29 | Differentiator is de-duplication into the graph, not extraction
243 | O. AI & intelligent automation | AI control-to-framework mapping with confidence scoring | D | Partial | Absent | P2 | WP-02, WP-28, WP-29
244 | O. AI & intelligent automation | AI regulatory change interpretation and impact analysis | D | Partial | Mock | P3 | WP-02, WP-28, WP-29 | ai/regulatory-pulse is mt_rand-backed
245 | O. AI & intelligent automation | AI-drafted policies, risk statements, findings and reports in house style | D | Partial | Partial | P2 | WP-02, WP-28, WP-29 | 7 LLM endpoints exist; only Risk Statement Builder is UI-wired
246 | O. AI & intelligent automation | AI summarisation of long-form content | D | Partial | Partial | P3 | WP-02, WP-28, WP-29
247 | O. AI & intelligent automation | Agentic workflows — evidence collector, chaser, triager, tester | LE | Partial | Absent | P3 | WP-02, WP-28, WP-29
248 | O. AI & intelligent automation | Agent governance — declared scope, approval thresholds, action log, kill switch | LE | Partial | Absent | P3 | WP-02, WP-28, WP-29 | 'We govern our own agents with the machinery we sell you'
249 | O. AI & intelligent automation | AI-assisted RCSA with inconsistency and boilerplate detection | LE | Partial | Absent | P2 | WP-02, WP-28, WP-29 | Almost nobody does this well
250 | O. AI & intelligent automation | Emerging risk horizon scanning linked to internal objectives | LE | Partial | Mock | P3 | WP-02, WP-28, WP-29 | ai/radar is mt_rand-backed
251 | O. AI & intelligent automation | Predictive risk modelling — likelihood of loss, slippage, control failure | LE | Partial | Mock | P0 | WP-02, WP-28, WP-29 | FABRICATED: hardcoded [0.87,0.73,...] and accuracy 87.3 / auc 0.912 / model_version 2.4.1
252 | O. AI & intelligent automation | AI-assisted configuration | D | Partial | Absent | P3 | WP-02, WP-28, WP-29
253 | O. AI & intelligent automation | Full AI traceability — sources, prompt, model, version | TS | Partial | Absent | P0 | WP-02, WP-28, WP-29 | Non-negotiable before any AI ships
254 | O. AI & intelligent automation | Human-in-the-loop approval gates on consequential AI actions | TS | Partial | Absent | P0 | WP-02, WP-28, WP-29
255 | O. AI & intelligent automation | AI output confidence scoring with routing to human review | D | Partial | Absent | P2 | WP-02, WP-28, WP-29
256 | O. AI & intelligent automation | AI governance module — inventory, EU AI Act, ISO 42001, drift, model cards | LE | Partial | Absent | P3 | WP-02, WP-28, WP-29 | Fastest-growing greenfield in GRC; King V requires it explicitly
257 | O. AI & intelligent automation | Configurable AI — model choice, per-feature opt-out, data residency control | D | Partial | Partial | P2 | WP-02, WP-28, WP-29 | Driver/model/endpoint configurable; no per-feature opt-out
258 | O. AI & intelligent automation | MCP server / agent-callable API | LE | Partial | Absent | P3 | WP-02, WP-28, WP-29
259 | P. Integration & data | REST API covering the full object model | TS | Yes | Absent | P1 | WP-07 | routes/api.php DOES NOT EXIST
260 | P. Integration & data | GraphQL API for graph traversal | D | Partial | Absent | P3 | WP-07
261 | P. Integration & data | OpenAPI specification and interactive API docs | TS | Yes | Absent | P1 | WP-07
262 | P. Integration & data | API versioning with a published deprecation policy | TS | Yes | Absent | P2 | WP-07
263 | P. Integration & data | Webhooks / outbound event streaming | TS | Yes | Absent | P1 | WP-07 | domain_events outbox exists but has no outbound transport
264 | P. Integration & data | OAuth 2.0 / OIDC for API auth | TS | Yes | Absent | P1 | WP-07 | No Sanctum, no Passport
265 | P. Integration & data | SAML 2.0 / OIDC SSO and SCIM provisioning | TS | Yes | Absent | P0 | WP-07 | No SSO of any kind; single local password store
266 | P. Integration & data | Bulk import/export with validation, staging and rollback | TS | Yes | Partial | P1 | WP-07 | CSV insert-only; no dry-run, no rollback; xlsx silently mis-parsed
267 | P. Integration & data | Embedded ETL with scheduling, transformation, error handling | TS | Yes | Absent | P2 | WP-07 | Corporater's ETL Transformer is genuinely capable
268 | P. Integration & data | Pre-built connector library | D | Partial | Absent | P2 | WP-07 | Corporater's real gap too — a window for us
269 | P. Integration & data | Regulatory and risk content feed integrations | D | Partial | Absent | P3 | WP-07
270 | P. Integration & data | Email, Teams and Slack task completion without entering the platform | D | Partial | Absent | P2 | WP-07 | High leverage for first-line adoption
271 | P. Integration & data | CDC / streaming ingestion for near-real-time control monitoring | LE | Partial | Absent | P3 | WP-07
272 | P. Integration & data | Data lineage and quality monitoring (BCBS 239) | D | Partial | Absent | P3 | WP-07
273 | P. Integration & data | Semantic/metrics layer for consistent definitions | D | Partial | Absent | P2 | WP-07 | The measure engine is this layer
274 | P. Integration & data | Sandbox environment with production-like data masking | D | Partial | Absent | P3 | WP-07
275 | Q. UX, configurability & accessibility | No-code field and form builder with conditional visibility | TS | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13
276 | Q. UX, configurability & accessibility | No-code object type builder | D | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13
277 | Q. UX, configurability & accessibility | No-code relationship builder | D | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13
278 | Q. UX, configurability & accessibility | BPMN 2.0 visual workflow designer with parallel, timers, escalation, SLA | TS | Yes | Partial | P1 | WP-05, WP-08, WP-09, WP-13 | Linear JSON stages only; escalation_rules stored and never read; delegate/escalate/return logged but change nothing
279 | Q. UX, configurability & accessibility | Out-of-office delegation and automatic reassignment | D | Yes | Absent | P2 | WP-05, WP-08, WP-09, WP-13
280 | Q. UX, configurability & accessibility | No-code dashboard and widget builder | TS | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13
281 | Q. UX, configurability & accessibility | Role-conditional page composition | D | Yes | Absent | P2 | WP-05, WP-08, WP-09, WP-13
282 | Q. UX, configurability & accessibility | 'My Responsibilities' personal work queue from ownership relationships | D | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13 | THE highest-leverage adoption feature
283 | Q. UX, configurability & accessibility | Org-node landing pages ('Business HQ') — navigate by entity, not module | LE | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13 | Inverts the navigation model; how executives actually think
284 | Q. UX, configurability & accessibility | Lightweight first-line experience optimised for 60-second interactions | D | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13 | Archer Engage exists because the main UI is too heavy for occasional users
285 | Q. UX, configurability & accessibility | Native mobile / offline capture with photo and GPS | D | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13 | In Nigeria this is also a connectivity and power requirement
286 | Q. UX, configurability & accessibility | Global search across all object types with permission filtering | TS | Yes | Absent | P1 | WP-05, WP-08, WP-09, WP-13
287 | Q. UX, configurability & accessibility | Saved views, filters and personal favourites | TS | Yes | Absent | P2 | WP-05, WP-08, WP-09, WP-13 | data-table component is 520 bytes; ~25 index views hand-roll filtering
288 | Q. UX, configurability & accessibility | In-app guidance, tooltips and contextual help | TS | Yes | Absent | P2 | WP-05, WP-08, WP-09, WP-13 | Risk maturity is the constraint — guidance matters more here than elsewhere
289 | Q. UX, configurability & accessibility | WCAG 2.2 AA accessibility | D | Yes | Absent | P2 | WP-05, WP-08, WP-09, WP-13
290 | Q. UX, configurability & accessibility | Full localisation including RTL and per-user language | D | Yes | Absent | P2 | WP-05, WP-08, WP-09, WP-13 | No lang/ directory; N symbol hardcoded in 28 views
291 | R. Security, administration & platform governance | RBAC with granular object, field and record-level permissions | TS | Yes | Partial | P0 | WP-00, WP-05, WP-30 | 46 permissions and 9 roles SEEDED; 0 routes use permission middleware; 9 @can across 5 of 142 views
292 | R. Security, administration & platform governance | Attribute-based / relationship-derived access control | D | Yes | Absent | P0 | WP-00, WP-05, WP-30 | Node-scoped authorization
293 | R. Security, administration & platform governance | Segregation of duties enforcement within the platform | TS | Yes | Partial | P1 | WP-00, WP-05, WP-30 | Tester/reviewer separation enforced by Gates in control testing only
294 | R. Security, administration & platform governance | Complete, tamper-evident audit log of all user and system actions | TS | Yes | Partial | P0 | WP-00, WP-05, WP-30 | risk_audit_trail exists but is mutable and the read path is broken
295 | R. Security, administration & platform governance | MFA, session management and password/IdP policy enforcement | TS | Yes | Partial | P0 | WP-00, WP-05, WP-30 | EnsureMfaVerified exists, is NOT aliased and is on NO route
296 | R. Security, administration & platform governance | Encryption in transit and at rest; documented key management | TS | Yes | Partial | P1 | WP-00, WP-05, WP-30
297 | R. Security, administration & platform governance | Customer-managed encryption keys (BYOK) | D | Yes | Absent | P3 | WP-00, WP-05, WP-30
298 | R. Security, administration & platform governance | Data residency options by region | TS | Yes | Absent | P0 | WP-00, WP-05, WP-30 | CBN localisation deadline: 1 January 2027
299 | R. Security, administration & platform governance | SOC 2 Type II / ISO 27001 certification; pen test reports | TS | Yes | Absent | P2 | WP-00, WP-05, WP-30
300 | R. Security, administration & platform governance | Application security verification and secure SDLC evidence | D | Yes | Absent | P2 | WP-00, WP-05, WP-30 | Corporater is VL5 Veracode Verified
301 | R. Security, administration & platform governance | Documented RTO/RPO, DR testing, backup/restore procedures | TS | Yes | Absent | P2 | WP-00, WP-05, WP-30 | Corporater publishes a 24-hour RTO
302 | R. Security, administration & platform governance | Configurable retention, legal hold and defensible deletion | TS | Yes | Absent | P2 | WP-00, WP-05, WP-30 | NDPA requirement
303 | R. Security, administration & platform governance | GDPR/NDPA support — DSAR handling, ROPA, data minimisation | TS | Yes | Absent | P2 | WP-00, WP-05, WP-30 | NDPA 2023 + GAID 2025 — a wedge product for the public sector
304 | R. Security, administration & platform governance | Admin console with usage analytics and adoption metrics | D | Yes | Absent | P2 | WP-00, WP-05, WP-30 | Adoption metrics predict renewal
305 | R. Security, administration & platform governance | Configuration change audit with rollback | D | Yes | Absent | P2 | WP-00, WP-05, WP-30
306 | R. Security, administration & platform governance | Environment promotion pipeline with automated configuration testing | LE | Yes | Absent | P3 | WP-00, WP-05, WP-30
307 | S. Deployment, delivery & commercial | SaaS multi-tenant delivery | TS | Yes | Partial | P1 | WP-16, WP-30 | Tenancy exists in the schema but is not enforced
308 | S. Deployment, delivery & commercial | Deployment choice — SaaS, private cloud, on-premise | D | Partial | Partial | P0 | WP-16, WP-30 | Claimed; undermined by CDN asset loading. CBN deadline 1 Jan 2027
309 | S. Deployment, delivery & commercial | Documented, predictable upgrade path with no config loss | TS | Yes | Absent | P2 | WP-16, WP-30
310 | S. Deployment, delivery & commercial | Accelerator / starter content packs for rapid time-to-value | D | Partial | Absent | P1 | WP-16, WP-30 | THE number-one reason global tools get bought and abandoned here
311 | S. Deployment, delivery & commercial | Fixed-price implementation option | D | Partial | Absent | P3 | WP-16, WP-30 | LogicManager's differentiator
312 | S. Deployment, delivery & commercial | Published, transparent pricing including AI feature pricing | D | Partial | Absent | P2 | WP-16, WP-30 | Naira, flat or entity-tiered, NEVER per-seat
313 | S. Deployment, delivery & commercial | Customer success, training and certification programme | TS | Yes | Absent | P2 | WP-16, WP-30 | Risk maturity is the constraint, not features
314 | S. Deployment, delivery & commercial | Public product documentation, API reference and developer portal | D | Partial | Absent | P2 | WP-16, WP-30 | Corporater's own weakness — a window
315 | S. Deployment, delivery & commercial | Active user community and partner ecosystem | D | Partial | Absent | P3 | WP-16, WP-30 | Partner with Big Four and local risk advisory rather than compete
316 | S. Deployment, delivery & commercial | Configuration marketplace for community-built packs | LE | Partial | Absent | P3 | WP-16, WP-30
343 | B. Risk taxonomy, register & appetite | Four-strategy risk response including risk SHARING as distinct from transfer | TS | Yes | Partial | P1 | WP-10 | treatment_plans.strategy is a free string (avoid/mitigate/transfer/accept). Sharing — JV, consortium, co-insurance, syndication — is a distinct response with its own counterparty and residual profile
344 | B. Risk taxonomy, register & appetite | One register spanning operational to strategic risk with type-specific attributes | TS | Yes | Partial | P1 | WP-10 | risk_level enum exists (granular/intermediate/enterprise) but strategic risks carry no distinct attributes, horizon or objective linkage
345 | C. Assessment, analysis & methodology | Treasury / ALM assessment perspective (IRRBB, liquidity, FX, counterparty) | D | Yes | Absent | P1 | WP-11, WP-16 | Named explicitly by Corporater. Direct CBN relevance — IRRBB is a Pillar 2 risk type in the ICAAP model we already have
346 | M. Strategy & performance | Project and portfolio as first-class risk-bearing nodes | D | Yes | Absent | P2 | WP-03, WP-27 | Corporater tracks treatments and controls across projects and portfolios, not only org units
347 | M. Strategy & performance | KRI tolerance managed in the context of strategic objectives | D | Yes | Absent | P2 | WP-27 | Requires an objectives model; distinct from risk-to-objective linkage
348 | N. Reporting, dashboards & analytics | Reporting governance object — responsibility, periodicity, threshold, format per report | D | Yes | Absent | P2 | WP-12 | Corporater frames standardised reporting as a governed process, not a template library. This is what an examiner asks to see
349 | R. Security, administration & platform governance | Risk-function resource adequacy evidence (people and technology) | D | Yes | Absent | P3 | WP-24 | Corporater names it as a compliance-demonstration benefit. Regulators ask at examination; essentially nobody models it
350 | A. Platform architecture & data model | Single-platform extension to compliance, incident, performance and internal audit | D | Yes | Absent | P1 | WP-03, WP-05 | The integrated-GRC promise. Only achievable on the object graph — the architecture bet restated as a customer benefit
317 | T. Nigeria & Africa environment (our own domain) | Offline-first architecture with deterministic conflict resolution | LE | No | Absent | P1 | WP-13 | ~190m mobile subs vs ~110m broadband; branch staff on metered 2G/3G they pay for
318 | T. Nigeria & Africa environment (our own domain) | PWA, installable, low-bandwidth (<200 KB initial, <3 s FMP at 2G) | LE | No | Absent | P1 | WP-13
319 | T. Nigeria & Africa environment (our own domain) | Autosave and power-cut resilience on every form | LE | No | Absent | P1 | WP-13 | Grid collapsed again in 2026; ~70% of businesses on generators
320 | T. Nigeria & Africa environment (our own domain) | USSD front-line capture | LE | No | Absent | P2 | WP-14 | Works without data or a smartphone. NO global vendor does this
321 | T. Nigeria & Africa environment (our own domain) | WhatsApp front-line capture with media | LE | No | Absent | P2 | WP-14 | WhatsApp banking launching actively in Nigeria
322 | T. Nigeria & Africa environment (our own domain) | Local-language intake flows (Hausa, Yoruba, Pidgin) | D | No | Absent | P3 | WP-14 | Belongs on the intake layer, not the platform UI
323 | T. Nigeria & Africa environment (our own domain) | Naira-native multi-currency with CBN official / NAFEM / parallel rate types | D | No | Absent | P1 | WP-15 | loss_events.currency is the only currency field and is unused
324 | T. Nigeria & Africa environment (our own domain) | Inflation-indexed threshold formulas with re-baselining approval | LE | No | Absent | P1 | WP-15 | Fixes the 'everything is High' drift; inflation 15.91% June 2026
325 | T. Nigeria & Africa environment (our own domain) | Rating drift report at re-baselining | LE | No | Absent | P2 | WP-15 | The annual conversation a Nigerian CRO needs with the board
326 | T. Nigeria & Africa environment (our own domain) | Nigeria-resident deployment tier with residency attestation | TS | No | Absent | P0 | WP-30 | CBN PSS/DIR/PUB/CIR/001/004: all payment data in Nigeria by 1 Jan 2027
327 | T. Nigeria & Africa environment (our own domain) | Naira pricing, locally invoiced, flat or entity-tiered (never per-seat) | D | No | Absent | P1 | WP-30 | Per-seat pricing structurally kills front-line capture
328 | T. Nigeria & Africa environment (our own domain) | CBN prudential obligation library and returns calendar | D | No | Partial | P1 | WP-16 | RegulatoryThresholdService encodes real citations and clocks — a genuine head start
329 | T. Nigeria & Africa environment (our own domain) | ICAAP as a first-class object with April deadline workflow | D | No | Partial | P1 | WP-16 | icaap_assessments is correctly structured; Pillar 2 values are inputs, not derived
330 | T. Nigeria & Africa environment (our own domain) | CBN cyber returns calendar (24h BSD, 28 Feb CSAT, monthly CTI by the 5th) | D | No | Absent | P1 | WP-16
331 | T. Nigeria & Africa environment (our own domain) | CBN-mandated org structure modelled (CISO->MD/CEO, ISSC, Board Risk/Audit) | D | No | Absent | P2 | WP-16
332 | T. Nigeria & Africa environment (our own domain) | NFIU STR/CTR clocks and thresholds | D | No | Strong | P3 | - | 24-hour NFIU clock and thresholds already encoded
333 | T. Nigeria & Africa environment (our own domain) | NDPA 2023 + GAID 2025 module (72h breach, DPIA, CAR, DPO CPD, ROPA) | D | No | Partial | P1 | WP-17 | issues.ndpa_reportable exists; no module. SGF Circular 59805 = hundreds of MDA buyers
334 | T. Nigeria & Africa environment (our own domain) | NAICOM risk-based capital / ORSA-equivalent | D | No | Absent | P2 | WP-17 | ~43 insurers recapitalised 31 Jul 2026; NO INCUMBENT SOFTWARE
335 | T. Nigeria & Africa environment (our own domain) | PenCom monthly high-risk extract (7 days post month-end) | D | No | Absent | P2 | WP-17 | That specific cadence is a product feature, not a config option
336 | T. Nigeria & Africa environment (our own domain) | FRC IFRS S1/S2 three-stage readiness workflow | D | No | Absent | P2 | WP-26 | Mandatory for PIEs from 1 Jan 2028; nobody else has built this
337 | T. Nigeria & Africa environment (our own domain) | Host-community / HCDT 3% opex module for extractives | D | No | Absent | P3 | WP-17 | No global product models a Nigerian host community trust
338 | T. Nigeria & Africa environment (our own domain) | Nigerian risk taxonomy (insecurity, diesel, FX repatriation, agents, cash-in-transit) | D | No | Absent | P1 | WP-16 | No global ERM taxonomy models these
339 | T. Nigeria & Africa environment (our own domain) | Multi-entity, multi-licence, multi-regulator group modelling | D | No | Absent | P1 | WP-03, WP-16 | A Nigerian holdco faces CBN, SEC, NAICOM, PenCom, NDPC concurrently
340 | T. Nigeria & Africa environment (our own domain) | Country packs — Ghana (BoG), Kenya (CBK), South Africa (King V, PA, POPIA) | D | No | Absent | P3 | WP-17 | King V disclosure statements per RECOMMENDED PRACTICE, not just principle

## Corporater Parity
Corporater ERM — published feature list, scored
The 45+ features Corporater publishes for its Enterprise Risk Management solution. This is the Phase 2 parity target.
# | Corporater feature | Our current state | Priority | Work package | Note
1 | Access control / permissions | Partial | P0 | WP-00 | Seeded but unenforced — 0 of 203 routes guarded
2 | Alerts and notifications | Partial | P2 | WP-07 | In-app + DB only; email is a logged placeholder
3 | Alignment with strategic initiatives, objectives and performance goals | Absent | P2 | WP-27 | No objectives model — the 'P' in Corporater's GPRC
4 | Audit log | Partial | P0 | WP-00, WP-01 | Exists, mutable, and the read path is broken
5 | Automated risk reporting | Partial | P0 | WP-12 | On-screen views only; CSV the sole file output; no PDF, no scheduling
6 | Automated workflows | Partial | P1 | WP-06 | Linear stages; escalation stored and never read
7 | Business continuity planning | Absent | P2 | WP-23
8 | Control activities | Present | P3 | - | Control library + testing is genuinely strong
9 | Customisable branding | Absent | P2 | WP-00 | Brand colours inline in the layout
10 | Data integration (automated and manual) | Partial | P1 | WP-07 | Manual CSV only; no connectors
11 | Data visualisation | Partial | P1 | WP-08 | Chart.js from CDN, server-fed, no interactivity
12 | Digital twin configuration | Partial | P1 | WP-03 | entities/entity_types is embryonic; parallel to business_units
13 | Document management | Partial | P2 | WP-12 | Read-only aggregator view
14 | Integrated governance/assurance (AML, Basel & Solvency, InfoSec & Privacy) | Partial | P1 | WP-16, WP-17 | AML and Basel present; Solvency and privacy absent
15 | Improvement database | Present | P3 | - | Issues + treatments + RCA actions cover this
16 | Incident management incl. loss/near-loss events | Strong | P3 | - | BEST-IN-CLASS. Exceeds Corporater.
17 | Integration with underlying risks and information systems | Absent | P1 | WP-07 | No API, no connectors
18 | Intuitive user interface | Partial | P1 | WP-09 | Server-rendered Blade; no inline edit, no bulk actions, no saved views
19 | KRI catalog | Present | P2 | WP-04 | Strong definitions; no breach register
20 | KRIs, KPIs and other metrics | Partial | P1 | WP-04 | KRI half only; unify under the measure engine
21 | Operational risk governance per compliance standards and taxonomies | Present | P2 | WP-16 | Basel + CBN ORMS dual taxonomy is a real strength
22 | Opportunity AND consequence heat maps | Partial | P1 | WP-10, WP-08 | Consequence only; NO opportunity model at all
23 | Policy management for operational risk policies | Absent | P2 | WP-21
24 | RegTech connectors | Absent | P2 | WP-07
25 | Risk analysis (scenario, correlation, sensitivity) | Partial | P2 | WP-18, WP-19 | Correlation column exists with no implementation; no sensitivity
26 | Risk analysis templates | Absent | P2 | WP-16 | Ship as content packs
27 | Risk appetite | Partial | P1 | WP-10 | Category-level only; service reads 5 non-existent columns
28 | Risk assessment perspectives (asset, process, external, operational scenario, legal, treasury) | Absent | P1 | WP-03, WP-10 | Assessment contexts with their own ID series and their own ID prefixes (AML-027, BSL2-01, SOD019) — see the screenshots. Treasury/ALM is the one perspective with direct CBN relevance we had not scoped.
29 | Risk assessments, internal and external, qualitative and quantitative | Present | P2 | WP-11 | Qualitative strong; quantitative exists but is separate
30 | Risk-bearing capability | Partial | P2 | WP-10, WP-19 | ICAAP capital model exists; not expressed as appetite capacity
31 | Risk consolidation and aggregation from internal and external sources | Partial | P1 | WP-03, WP-07 | Internal roll-up only
32 | Risk context | Partial | P1 | WP-10 | ISO 31000 scope/context/criteria not modelled
33 | Risk Control Self-Assessment (RCSA) | Partial | P0 | WP-02, WP-11 | storeWorksheet() IS A STUB — submissions discarded
34 | Risk dashboards | Partial | P1 | WP-08 | ONE fixed 48.6 KB dashboard
35 | Risk data upload via integration and manual input | Partial | P1 | WP-07 | CSV insert-only; xlsx silently mis-parsed
36 | Risk evaluation | Present | P2 | WP-05 | Hardcoded 5x5 and rating bands
37 | Risk framework support (ISO 31000, COSO, ISO 27005) | Absent | P1 | WP-17 | No framework model at all
38 | Risk heat maps | Partial | P1 | WP-08 | Hardcoded 5x5, no cell counts, no drill-through
39 | Risk identification (manual and bulk import) based on taxonomy | Present | P2 | -
40 | Risk mitigation workflows | Present | P2 | WP-06 | Treatment lifecycle is complete; 19 duplicate columns
41 | Risk modeling | Partial | P2 | WP-18
42 | Risk monitoring | Present | P2 | WP-04
43 | Risk probability distribution and simulation incl. Monte Carlo | Present | P1 | WP-18 | Poisson-Lognormal only; runs synchronously in the HTTP request
44 | Risk radar | Mock | P0 | WP-02 | mt_rand-generated. REMOVE IMMEDIATELY.
45 | Risk register | Strong | P3 | -
46 | Risk reporting | Partial | P0 | WP-12 | CSV only
47 | Risk response | Present | P3 | -
48 | Risk taxonomies | Present | P1 | WP-10 | One taxonomy in use; a second is orphaned; no multi-taxonomy
49 | Risk treatment | Strong | P3 | -
50 | SSO | Absent | P0 | WP-00 | None of any kind
51 | Strategic risk management | Absent | P2 | WP-27
52 | Surveys | Partial | P1 | WP-11 | Schema ahead of market; UI is 915 bytes
53 | Third-party risk management | Absent | P2 | WP-22
54 | Version control | Absent | P1 | WP-03 | Field-level audit only; no entity versioning or point-in-time
55 | Link risks to assurance frameworks across the three lines of defense | Absent | P2 | WP-24 | Benefits prose. Assurance mapping with coverage and gap view.
56 | Correlate risk profile, impact and RISK MATURITY with performance and objectives | Absent | P2 | WP-11, WP-27 | Benefits prose. Risk maturity is a scored, trended assessment, not a label.
57 | Track treatments and controls across PROJECTS and PORTFOLIOS, not just org units | Absent | P2 | WP-03 | Benefits prose. Project and Portfolio must be first-class risk-bearing node types.
58 | Four risk responses: avoidance, reduction, SHARING, transfer | Partial | P1 | WP-10 | Benefits prose. We have avoid/mitigate/transfer/accept as a free string. 'Sharing' (joint venture, consortium, co-insurance) is distinct from transfer and unmodelled.
59 | Automated aggregation of risks UP THE CHAIN | Partial | P1 | WP-03, WP-04 | Benefits prose. Risk::calculateRollUpScore() is risk-specific; graph-derived roll-up is not.
60 | One shared dynamic register spanning OPERATIONAL to STRATEGIC risk | Partial | P1 | WP-10 | Benefits prose. risk_level enum exists (granular/intermediate/enterprise) but strategic risk carries no distinct attributes.
61 | KRIs managed against tolerance IN THE CONTEXT OF strategic objectives | Absent | P2 | WP-27 | Benefits prose. Requires an objectives model; KRI-to-objective is distinct from risk-to-objective.
62 | Standardised reporting process: responsibilities, periodicity, thresholds, formats | Absent | P2 | WP-12 | Benefits prose. A reporting-governance object, not just a report template.
63 | Evidence of sufficient resources (people and technology) for proactive risk management | Absent | P3 | WP-24 | Benefits prose. Regulators ask this at examination; nobody models it.
64 | Extendable to compliance, incident, performance and internal audit in ONE system | Absent | P1 | WP-03, WP-05 | The integrated-GRC promise. Only achievable on the object graph — this is the architecture bet stated as a customer benefit.
| Total features | 64
| Strong or Present | 15
| Partial | 28
| Absent or Mock | 21
| Weighted parity | 38.2%

## P0-P1 Backlog
P0 and P1 backlog — the critical path
P0 = blocker (unsellable/unsafe until fixed). P1 = required for Corporater parity. Sorted P0 first, then by work package.
Priority | Work package | Domain | Capability | Current state | Evidence / note
P0 | WP-00 | A. Platform architecture & data model | Multi-entity / multi-org support with data segregation | Partial | organization_id on every table but ZERO global scopes; 166 uses of '?? 1' across 22 files; MonteCarloService line 49 reads scenarios with no org filter
P0 | WP-00, WP-03 | A. Platform architecture & data model | Full versioning and immutable audit trail on every object and field | Partial | Field-level trail exists but is broken: AuditTrailService writes 'Risk', Risk::auditTrail() queries 'risk'
P0 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | RBAC with granular object, field and record-level permissions | Partial | 46 permissions and 9 roles SEEDED; 0 routes use permission middleware; 9 @can across 5 of 142 views
P0 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | Attribute-based / relationship-derived access control | Absent | Node-scoped authorization
P0 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | Complete, tamper-evident audit log of all user and system actions | Partial | risk_audit_trail exists but is mutable and the read path is broken
P0 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | MFA, session management and password/IdP policy enforcement | Partial | EnsureMfaVerified exists, is NOT aliased and is on NO route
P0 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | Data residency options by region | Absent | CBN localisation deadline: 1 January 2027
P0 | WP-02, WP-11 | C. Assessment, analysis & methodology | RCSA with full lifecycle (scope, distribute, respond, challenge, sign-off) | Partial | RcsaController::storeWorksheet() IS A STUB — submissions silently discarded
P0 | WP-02, WP-28, WP-29 | O. AI & intelligent automation | Predictive risk modelling — likelihood of loss, slippage, control failure | Mock | FABRICATED: hardcoded [0.87,0.73,...] and accuracy 87.3 / auc 0.912 / model_version 2.4.1
P0 | WP-02, WP-28, WP-29 | O. AI & intelligent automation | Full AI traceability — sources, prompt, model, version | Absent | Non-negotiable before any AI ships
P0 | WP-02, WP-28, WP-29 | O. AI & intelligent automation | Human-in-the-loop approval gates on consequential AI actions | Absent
P0 | WP-07 | P. Integration & data | SAML 2.0 / OIDC SSO and SCIM provisioning | Absent | No SSO of any kind; single local password store
P0 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Export to PDF, Word, Excel, PowerPoint | Absent | NO PDF ANYWHERE. Board/regulatory/executive reports render as on-screen views only; generateCustom validates pdf,excel,html,pptx then collapses all four to CSV
P0 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Board pack generation — narrative plus visuals, versioned and approved | Absent
P0 | WP-16, WP-30 | S. Deployment, delivery & commercial | Deployment choice — SaaS, private cloud, on-premise | Partial | Claimed; undermined by CDN asset loading. CBN deadline 1 Jan 2027
P0 | WP-30 | T. Nigeria & Africa environment (our own domain) | Nigeria-resident deployment tier with residency attestation | Absent | CBN PSS/DIR/PUB/CIR/001/004: all payment data in Nigeria by 1 Jan 2027
P1 | - | I. Incidents, events, issues & actions | Incident capture with configurable forms and multi-channel intake | Present | Web only today; USSD/WhatsApp is WP-14
P1 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | Segregation of duties enforcement within the platform | Partial | Tester/reviewer separation enforced by Gates in control testing only
P1 | WP-00, WP-05, WP-30 | R. Security, administration & platform governance | Encryption in transit and at rest; documented key management | Partial
P1 | WP-02, WP-07 | A. Platform architecture & data model | Bulk import/export at object level with validation and error reporting | Partial | CSV only; xlsx accepted but parsed with fgetcsv; insert-only, no dry-run, no rollback
P1 | WP-02, WP-10 | B. Risk taxonomy, register & appetite | Emerging risk register distinct from the principal register | Mock | ai/radar page is mt_rand-generated
P1 | WP-03 | A. Platform architecture & data model | Configurable, typed relationships between any object types | Absent | Relationships are hardcoded pivots
P1 | WP-03 | A. Platform architecture & data model | Digital-twin org graph (entity, division, BU, process, system, asset, product, geography) | Partial | entities/entity_types is an embryonic version; runs in parallel with business_units — two org models
P1 | WP-03 | A. Platform architecture & data model | Object inheritance/templating so common behaviour is defined once | Absent
P1 | WP-03 | A. Platform architecture & data model | Hierarchical roll-up and aggregation derived from the graph | Partial | Risk::calculateRollUpScore() exists but is risk-specific, not graph-derived
P1 | WP-03 | A. Platform architecture & data model | Configurable lifecycle states and status models per object type | Absent | Status is a hardcoded enum/string per table
P1 | WP-03, WP-05 | A. Platform architecture & data model | Metadata-driven object model; new fields without code deployment | Absent | No metadata layer; all fields are DDL columns
P1 | WP-03, WP-05 | A. Platform architecture & data model | Configurable object types (not just fields) | Absent | entity_types carries only icon/color/level — no attribute schema
P1 | WP-03, WP-05 | A. Platform architecture & data model | Single-platform extension to compliance, incident, performance and internal audit | Absent | The integrated-GRC promise. Only achievable on the object graph — the architecture bet restated as a customer benefit
P1 | WP-03, WP-16 | T. Nigeria & Africa environment (our own domain) | Multi-entity, multi-licence, multi-regulator group modelling | Absent | A Nigerian holdco faces CBN, SEC, NAICOM, PenCom, NDPC concurrently
P1 | WP-03, WP-20 | E. Controls & control monitoring | Common control model — one control satisfying N requirements, tested once | Absent | Requires typed relationships
P1 | WP-04 | A. Platform architecture & data model | Period-aware measure model shared by KPIs and KRIs | Absent | Risk scores are single-valued; no period dimension anywhere
P1 | WP-04 | A. Platform architecture & data model | Point-in-time reconstruction of any object's state ('as at' queries) | Absent | Reconstructable only indirectly from risk_assessments
P1 | WP-04, WP-05 | A. Platform architecture & data model | Calculated/derived fields with a formula engine | Absent | Needed for inflation-indexed thresholds
P1 | WP-04, WP-08 | C. Assessment, analysis & methodology | Heat map movement / trend visualisation across periods | Absent
P1 | WP-04, WP-27 | M. Strategy & performance | Unified KPI/KRI model on one period-aware measure engine | Partial | KRI half exists; KPI half does not. This is Corporater's 'P' in GPRC and their stated differentiator.
P1 | WP-05 | A. Platform architecture & data model | Multi-tenancy with per-tenant configuration divergence | Absent
P1 | WP-05 | B. Risk taxonomy, register & appetite | Central risk register with configurable fields | Present | Register is strong; fields are not configurable
P1 | WP-05 | B. Risk taxonomy, register & appetite | Configurable likelihood and consequence scales with definitions per point | Absent | 5x5 hardcoded in 3 places; settings written but read by nothing
P1 | WP-05 | D. Risk quantification | Semi-quantitative currency ranges on impact | Partial | financial_exposure_ngn exists; scale points carry no currency bands
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | No-code field and form builder with conditional visibility | Absent
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | No-code object type builder | Absent
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | No-code relationship builder | Absent
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | BPMN 2.0 visual workflow designer with parallel, timers, escalation, SLA | Partial | Linear JSON stages only; escalation_rules stored and never read; delegate/escalate/return logged but change nothing
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | No-code dashboard and widget builder | Absent
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | 'My Responsibilities' personal work queue from ownership relationships | Absent | THE highest-leverage adoption feature
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | Org-node landing pages ('Business HQ') — navigate by entity, not module | Absent | Inverts the navigation model; how executives actually think
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | Lightweight first-line experience optimised for 60-second interactions | Absent | Archer Engage exists because the main UI is too heavy for occasional users
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | Native mobile / offline capture with photo and GPS | Absent | In Nigeria this is also a connectivity and power requirement
P1 | WP-05, WP-08, WP-09, WP-13 | Q. UX, configurability & accessibility | Global search across all object types with permission filtering | Absent
P1 | WP-07 | P. Integration & data | REST API covering the full object model | Absent | routes/api.php DOES NOT EXIST
P1 | WP-07 | P. Integration & data | OpenAPI specification and interactive API docs | Absent
P1 | WP-07 | P. Integration & data | Webhooks / outbound event streaming | Absent | domain_events outbox exists but has no outbound transport
P1 | WP-07 | P. Integration & data | OAuth 2.0 / OIDC for API auth | Absent | No Sanctum, no Passport
P1 | WP-07 | P. Integration & data | Bulk import/export with validation, staging and rollback | Partial | CSV insert-only; no dry-run, no rollback; xlsx silently mis-parsed
P1 | WP-08 | E. Controls & control monitoring | Control effectiveness dashboards by entity, process and framework | Partial | testing-dashboard.blade.php is 4.7 KB
P1 | WP-08, WP-11 | C. Assessment, analysis & methodology | Heat maps with configurable axes, bubble sizing and drill-through | Partial | Hardcoded 5x5; no cell counts; no drill-through
P1 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Role-based dashboards with drill-down to source object | Absent | One 48.6 KB fixed dashboard; no roles, no drill-down
P1 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Context-bound widgets — one definition rendering per org node | Absent | The single biggest demo differentiator
P1 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Widget library — heat map, bubble, trend, gauge, table, treemap, network, Gantt | Partial | Chart.js from CDN, server-fed, ~8 chart types, no interactivity
P1 | WP-08, WP-12 | N. Reporting, dashboards & analytics | User-configurable personal dashboards | Absent
P1 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Report builder with templates, filters and parameters | Partial | reports/custom exists; validates 4 formats and emits CSV for all of them
P1 | WP-08, WP-12 | N. Reporting, dashboards & analytics | Period-over-period comparison and movement analysis | Absent | Requires the period model
P1 | WP-10 | B. Risk taxonomy, register & appetite | Configurable multi-level risk taxonomy (3+ levels) | Present | risk_categories: self-tree, level, materialized path, cbn_mapping_code, basel_category
P1 | WP-10 | B. Risk taxonomy, register & appetite | Multiple simultaneous taxonomies on one risk | Absent | One category_id only; risk_taxonomies is a disconnected parallel tree with its own live UI
P1 | WP-10 | B. Risk taxonomy, register & appetite | Cause -> risk event -> consequence structure | Absent | A risk is a title plus scores; ISO 31000 requires structure
P1 | WP-10 | B. Risk taxonomy, register & appetite | Opportunity modelling alongside threat (ISO 31000 bidirectional) | Absent | Corporater ships an opportunity heat map; we have no opportunity model at all
P1 | WP-10 | B. Risk taxonomy, register & appetite | Inherent, current/residual and target risk levels | Partial | target_rating is a STRING LABEL ONLY — no target L/I/score, so target cannot be plotted
P1 | WP-10 | B. Risk taxonomy, register & appetite | Risk appetite statements as first-class objects linked to objectives | Partial | Keyed to risk_category_id only; not linked to objectives or nodes
P1 | WP-10 | B. Risk taxonomy, register & appetite | Quantified appetite/tolerance thresholds with automatic breach detection | Partial | Single tolerance band; RiskAppetiteService reads 5 columns that do not exist - capacity, appetite_type and notes are always fallbacks
P1 | WP-10 | B. Risk taxonomy, register & appetite | Risk appetite cascade — group appetite decomposed to BU limits | Absent | entities.category_appetites exists but is unused
P1 | WP-10 | B. Risk taxonomy, register & appetite | Risk acceptance workflow with sign-off, expiry and re-review | Absent | treatment_strategy can be 'accept' with zero governance
P1 | WP-10 | B. Risk taxonomy, register & appetite | Four-strategy risk response including risk SHARING as distinct from transfer | Partial | treatment_plans.strategy is a free string (avoid/mitigate/transfer/accept). Sharing — JV, consortium, co-insurance, syndication — is a distinct response with its own counterparty and residual profile
P1 | WP-10 | B. Risk taxonomy, register & appetite | One register spanning operational to strategic risk with type-specific attributes | Partial | risk_level enum exists (granular/intermediate/enterprise) but strategic risks carry no distinct attributes, horizon or objective linkage
P1 | WP-11 | C. Assessment, analysis & methodology | Prior-period pre-population with change highlighting | Absent | Requires the period model
P1 | WP-11 | C. Assessment, analysis & methodology | Second-line challenge and override workflow | Absent
P1 | WP-11 | C. Assessment, analysis & methodology | Questionnaire builder with conditional logic, scoring and weighting | Partial | Schema is AHEAD of market (8 types, conditional_logic, scoring_rules); UI is 915 bytes
P1 | WP-11, WP-16 | C. Assessment, analysis & methodology | Treasury / ALM assessment perspective (IRRBB, liquidity, FX, counterparty) | Absent | Named explicitly by Corporater. Direct CBN relevance — IRRBB is a Pillar 2 risk type in the ICAAP model we already have
P1 | WP-12, WP-16 | F. Compliance, obligations & regulatory change | Regulatory reporting pack generation (ICAAP, ORSA, self-assessment) | Partial | ICAAP model exists; output is CSV
P1 | WP-13 | T. Nigeria & Africa environment (our own domain) | Offline-first architecture with deterministic conflict resolution | Absent | ~190m mobile subs vs ~110m broadband; branch staff on metered 2G/3G they pay for
P1 | WP-13 | T. Nigeria & Africa environment (our own domain) | PWA, installable, low-bandwidth (<200 KB initial, <3 s FMP at 2G) | Absent
P1 | WP-13 | T. Nigeria & Africa environment (our own domain) | Autosave and power-cut resilience on every form | Absent | Grid collapsed again in 2026; ~70% of businesses on generators
P1 | WP-15 | T. Nigeria & Africa environment (our own domain) | Naira-native multi-currency with CBN official / NAFEM / parallel rate types | Absent | loss_events.currency is the only currency field and is unused
P1 | WP-15 | T. Nigeria & Africa environment (our own domain) | Inflation-indexed threshold formulas with re-baselining approval | Absent | Fixes the 'everything is High' drift; inflation 15.91% June 2026
P1 | WP-16 | T. Nigeria & Africa environment (our own domain) | CBN prudential obligation library and returns calendar | Partial | RegulatoryThresholdService encodes real citations and clocks — a genuine head start
P1 | WP-16 | T. Nigeria & Africa environment (our own domain) | ICAAP as a first-class object with April deadline workflow | Partial | icaap_assessments is correctly structured; Pillar 2 values are inputs, not derived
P1 | WP-16 | T. Nigeria & Africa environment (our own domain) | CBN cyber returns calendar (24h BSD, 28 Feb CSAT, monthly CTI by the 5th) | Absent
P1 | WP-16 | T. Nigeria & Africa environment (our own domain) | Nigerian risk taxonomy (insecurity, diesel, FX repatriation, agents, cash-in-transit) | Absent | No global ERM taxonomy models these
P1 | WP-16, WP-30 | S. Deployment, delivery & commercial | SaaS multi-tenant delivery | Partial | Tenancy exists in the schema but is not enforced
P1 | WP-16, WP-30 | S. Deployment, delivery & commercial | Accelerator / starter content packs for rapid time-to-value | Absent | THE number-one reason global tools get bought and abandoned here
P1 | WP-17 | T. Nigeria & Africa environment (our own domain) | NDPA 2023 + GAID 2025 module (72h breach, DPIA, CAR, DPO CPD, ROPA) | Partial | issues.ndpa_reportable exists; no module. SGF Circular 59805 = hundreds of MDA buyers
P1 | WP-18 | D. Risk quantification | Monte Carlo engine with configurable iterations and seeds | Present | 10,000 iterations default; RUNS SYNCHRONOUSLY IN THE HTTP REQUEST; no seed control
P1 | WP-20 | E. Controls & control monitoring | Control-to-obligation/framework mapping, multi-framework | Absent
P1 | WP-20 | F. Compliance, obligations & regulatory change | Regulatory obligation register at requirement/clause level | Absent | regulatory_circulars tracks documents, not obligations
P1 | WP-20 | F. Compliance, obligations & regulatory change | Obligation -> policy -> control -> risk -> process linkage chain | Absent | The compliance spine
P1 | WP-20 | F. Compliance, obligations & regulatory change | Multi-framework support with cross-mapping | Partial | regulatory_risk_mapping exists; no framework model
P1 | WP-20 | F. Compliance, obligations & regulatory change | Regulatory interaction/examination management | Partial | issues.cbn_examination_finding exists; no examination object
P1 | WP-30 | T. Nigeria & Africa environment (our own domain) | Naira pricing, locally invoiced, flat or entity-tiered (never per-seat) | Absent | Per-seat pricing structurally kills front-line capture

## Legend
Legend and method
CURRENT STATE | Meaning | Weight in the weighted-coverage score
Strong | Best-in-class; exceeds or matches the benchmark | 1.00
Present | Implemented and usable; may need uplift | 0.85
Partial | Partially implemented, or schema exists without UI/behaviour | 0.40
Mock | Renders but the numbers are fabricated (mt_rand) — worse than absent | 0.05
Absent | Not implemented | 0.00
CLASS | Meaning
TS | Table stakes — absence disqualifies you from an evaluation
D | Differentiator — separates good products from average ones
LE | Leading edge — few vendors have it in 2026; where you can win
PRIORITY | Meaning | Phase
P0 | Blocker — unsellable or unsafe until fixed | Phase 0 (weeks 1-4)
P1 | Parity — required to match Corporater | Phases 1-2 (weeks 5-24)
P2 | Moat — where we win against every competitor | Phases 3-4 (weeks 21-44)
P3 | Beyond — valuable but deferrable | Later
CORPORATER | Meaning
Yes | Published in their solution feature list, brief or screenshots
Partial | Claimed but not evidenced in depth
No | Not offered
Unknown | Not evidenced publicly either way
SOURCES
Codebase | Full read of all 60 migrations, routes/web.php, composer.json, bootstrap, config, 4 middleware, 20 models, 10 of 14 services, seeders, and targeted controller method bodies, plus an independent adversarial verification pass over 42 specific factual claims.
Corporater | corporater.com/solution/enterprise-risk-management-software, the 4-page Enterprise Risk Management Solution Brief, and 12 product screenshots.
Benchmark | Riskonnect, MetricStream, Archer, IBM OpenPages, ServiceNow IRM, LogicManager, SAI360, Diligent, Resolver, Protecht, Camms, Origami, Workiva; Verdantix Green Quadrant GRC 2025, Gartner MQ GRC Tools 2025.
Standards | ISO 31000:2018, COSO ERM 2017, COSO IC 2013, ISO 27001:2022, ISO 27005, ISO 22301, ISO 37301, ISO 42001, NIST CSF 2.0, Basel II/III operational risk, Solvency II, IFRS S1/S2, TCFD, DORA, FAIR, IIA Three Lines 2020.
Nigeria / Africa | CBN circulars and guidelines, NDIC, SEC Nigeria, NAICOM, PenCom, NCC, NUPRC/NMDPRA, NERC, FRC, NDPA 2023 + GAID 2025, NITDA National Cloud Policy 2025, Bank of Ghana, CBK Kenya, King V South Africa, POPIA.